## CCB
Role | Responsibility
Product Engineering | Evaluate technical depth of the change and risk to product function.
System Engineering | Ensure change aligns with system-level requirements, design, and interfaces.
Manufacturing / Prototype | Assess impact on build processes, tooling, and manufacturability.
Quality | Evaluate risks to product quality, compliance, and warranty. Review historical field data if needed.
Purchasing | Determine supplier impact, cost, and timing implications.
Verification & Validation | Assess need for revalidation and testing of the change.
Program Management | Ensure timing, cost, and scope alignment with program goals.
Service / Warranty | Provide input on field issues and potential service impacts of the change.
Customer Interface (if applicable) | Ensure changes are aligned with customer requirements and contracts.